## English
ARABIAN MAINTENANCE OPERATION SERVICE
Arabian Maintenance Operation Service Co. Ltd.
Maintenance Faults – Building 326 (27–28 Sep 2026)
No. | Date | Dept | Location | Complaint | Status | Note
1 | 27/9/2026 | Plumbing | F98 | Sink blocked | Completed | -
2 | 27/9/2026 | Civil | S229 | Ceiling needs repair (opposite) | Completed | -
3 | 27/9/2026 | Electrical | S75 | Toilet – lighting not working | Waiting Parts | SPR
4 | 28/9/2026 | Plumbing | F (unclear) | socket needs closing | Waiting Parts | SPR
5 | 28/9/2026 | Civil | S26 | Private toilet needs repair and painting | Waiting Parts | SPR

## عربي
ARABIAN MAINTENANCE OPERATION SERVICE
Arabian Maintenance Operation Service Co. Ltd.
أعطال الصيانة – مبنى 326 (27–28 سبتمبر 2026)
رقم | التاريخ | القسم | الموقع | وصف العطل | الحالة | ملاحظة
1 | 27/9/2026 | سباكة | F98 | مغسلة مسدودة | منجزة | -
2 | 27/9/2026 | مدني | S229 | سقف يحتاج إصلاح (مقابل) | منجزة | -
3 | 27/9/2026 | كهرباء | S75 | دورة مياه – إضاءة لا تعمل | بانتظار القطع | SPR
4 | 28/9/2026 | سباكة | F (غير واضح) | مغسلة / حنفية تحتاج إغلاق | بانتظار القطع | SPR
5 | 28/9/2026 | مدني | S26 | دورة مياه خاصة تحتاج إصلاح ودهان | بانتظار القطع | SPR